## Slide 1
Pretoria
New York
London
Sydney
MarketSquare
Path to Launch
Wave 1 · Pretoria · New York · London · Sydney
April 2026
trustsquare.co

## Slide 2
Where We Are Now
April 2026 · Current State
693
Total Sellers
Live
5
Cities at
Threshold
11
Cities in
Pipeline
v1.2.0
BEA Backend
Live
Live & Working
+ Core marketplace (FEA + BEA)
+ Trust Score system
+ Advert Agent (AI Coach)
+ Tiered AI packs
+ Intro flow end-to-end
+ Photo storage (Cloudflare R2)
+ 4-level geo hierarchy
+ CityLauncher dashboard
+ Admin onboarding tool
Still To Do
-> Paystack live mode
-> n8n email notifications
-> Seller magic-link accept/decline
-> CIPC SA Pty Ltd registration
-> Sydney, Durban, Bloemfontein nearing threshold
-> Sydney pipeline: 52/60 sellers confirmed

## Slide 3
Project Timeline
8-Week Roadmap to Wave 1 Public Launch
W1
W2
W3
W4
W5
W6
W7
W8
Phase 1
Technical
W1–W2
Phase 2
Seller Pipeline
W2–W5
Phase 3
Payments Live
W3–W4
Phase 4
Pre-Launch
W5–W6
Phase 5
Wave 1 Launch
W7–W8
TODAY
Payments
Live ◆
60 Sellers
+ Soft Launch ◆
PUBLIC
LAUNCH ◆

## Slide 4
Critical Path to Launch
Three blockers that gate soft-launch
1
CIPC Registration
Unblocks Paystack live mode.
David action — already in progress.
Estimated completion: 2–4 weeks.
2
60 Founding Sellers
37 more sellers needed in Pretoria.
Masoushka + n8n SellerScraper pipeline.
Blocks city going public.
3
n8n Email Notifications
Sellers must receive intro requests.
N8N_WEBHOOK_NEW_INTRO env var + workflow.
Blocks real marketplace usage.
All three blockers must be resolved before soft-launch can proceed.

## Slide 5
City Pipeline · Launch Status
THRESHOLD MET ● 5 CITIES
Pretoria · ZA
62/60
New York · US
60/60
London · GB
63/60
Cape Town · ZA
65/60
Johannesburg · ZA
63/60
IN PROGRESS
Durban · ZA
58/60
Sydney · AU
52/60
Bloemfontein · ZA
54/60
East London · ZA
47/60
Port Elizabeth · ZA
40/60
Polokwane · ZA
14/60
Each city launches publicly once it hits 60 founding sellers. KPI auto-triggers public visibility on trustsquare.co/launch/

## Slide 6
Launch Readiness · Go/No-Go Criteria
TECHNICAL
BEA backend stable
Intro flow end-to-end
Photo upload + storage
Trust Score system
n8n email notifications
Seller magic-link accept/decline
Anthropic billing active
COMMERCIAL
Paystack test mode
CIPC registration
Paystack live mode
International entity (NY/LON/SYD)
CONTENT
60 founding sellers (Pretoria)
60 sellers each (NY · LON · SYD)
Real listing content + photos

## Slide 7
Launch Day
What Happens
1
KPI fires
60 sellers confirmed
across all 4 cities
2
Paystack live
Real 1T intro fees
charged to buyers
3
n8n alerts
Buyers & sellers
notified automatically
4
CityLauncher
All live cities shown
at trustsquare.co/launch/
trustsquare.co · The trusted anonymous marketplace

## Slide 8
Trust Score System
How buyers earn and maintain seller trust
TRUST TIERS
Highly Trusted
Score 90–100 · Gold Badge
Priority listing · discounted commission
Trusted
Score 70–89 · Green Badge
Standard listing · full features
Established
Score 40–69 · Blue Badge
Building reputation · limited boosts
New
Score 0–39 · No Badge
Unverified · restricted access
Penalties
Dispute lost: -10 pts
No-show: -5 pts · Fraud: -25 pts
Universal Score
30 pts total · All categories
Verified Identity +20
ID verified by admin
Profile Complete +15
Photo, bio, contact filled
Payment Method +10
Bank / card linked
Active Subscription +5
Paid plan active
Track Record
30 pts total · Transaction history
Successful Txns +15
10+ completed deals
Positive Reviews +10
4.5+ star average
Response Rate +5
Responds within 24h
Account Longevity +5
1+ year active account
Category Credentials
40 pts total · Per category
Specialist Badge +8
Admin-verified expertise
Category Experience +6
5+ deals in category
Category Reviews +4
4.5+ in this category
Listing Quality +2
Complete photos + description
Repeat Buyers +0
Loyal buyer base
No self-reporting
Docs required
Reg numbers checked live
Real-time verification
Track record is system-only
No manual overrides
Server-side score only
Client cannot modify
Expired certs = 0 pts
Renew to restore points