## How to use
TrustSquare · Traceability Matrix Template
Purpose | One matrix per change. It proves no artifact was dropped: every change-item is checked off against every artifact that carries it.
Step 1 | Open a CHANGE-ID and fill the Term Map tab (old -> new for every word/rule/number/name). One row per distinct written form.
Step 2 | Walk the Artifact Classes tab; grep each class for the term-map 'search' values. Log hits.
Step 3 | For every (artifact x change-item) hit, add a row on the Matrix tab and drive Status to 'verified' or explicit 'N-A'.
The 100% rule | The change is NOT done until every Matrix row is 'verified' or 'N-A (reason)'. A blank/pending cell is a dropped item by definition.
Verified bar | Sensor grep returns ZERO surviving old tokens + Matrix is 100% + smoke_test.py green and served copies match HEAD.
Save as | MATRIX_CC-001.xlsx (etc). Keep this file as the blank template.
Canonical | CHANGE_CONTROL_PROTOCOL.md · active changes & term maps: CHANGE_REGISTER.md

## Term Map
TERM MAP — the mechanical key (one row per distinct old form)
Rows below are illustrative examples — delete them and enter this change's tokens.
old (exact) | new | kind | search (grep literal/regex) | notes / false-positive traps
AI Coach uses | Tuppence only (SKU retired) | concept | AI Coach uses | 5 outreach templates x2 repos
AI Coach Credits packs 5T=40 · 10T=100 · 25T=320 + ai_pack_sessions | per-use canon (Addendum 1 r10) | concept | 5T=40¦ai_pack_sessions | AGENT_BRIEFING 29/146-151
AI Pack (5T · 40 uses) | advanced-AI per-use copy | copy | AI Pack | marketsquare.html 3040
3 free AI sessions (credited) / ai_sessions: 3 | RETIRED — replacement copy AD-06 | concept | free AI sessions¦ai_sessions | html 2604/2607/2802/2805; ms.js 4238/4639; bea_main 1205/2610-21
ai_pack_sessions payment path | retire (Gate 2 staged diff) | endpoint | ai_pack_sessions | bea_main 3115-3249; ms.js 916/661
AI sessions remaining / Free AI session used | AI feature credits framing | copy | AI sessions remaining | admin 3783-84
briefing endpoint rows: initialize?ai_pack_sessions / AA session balance / buy-pack | 410-retired + per-use HOLD (ai-commit/ai-settle) | endpoint | buy-pack¦AA session | AGENT_BRIEFING 146-151; AA docs
Free $0 3/day · Starter $5/mo 20/day · Premium $15/mo 50/day (buyer tiers) | ONE 5-tier model $0/12/20/40/100; daily session limits retired (AD-07) | number | sessions per day¦\$5/mo¦\$15/mo | Codex tbl9; PR A7 x4; eula 527-535; html 2210-14; ms.js 11615
Seller tiers $0·2 / $5(R90)·20 / $15(R270)·50 | Free $0·2 / Standard $12·10 / Professional $20·25 / Business $40·60 / Elite $100·500 (slots=CAP) | number | R90¦R270¦Max concurrent | Codex §11.1; support 343-44; LISTING_STATE_MACHINE; Blueprint
Upgrade to Global · $5/mo | Upgrade · from $12/mo (verify microcopy) | copy | Global · \$5/mo | marketsquare.html 1120 — LIVE button
2 Tuppence per batch of 20 extra slots (§11.2) | UNRESOLVED — AD-08 | rule | per batch of 20 | predates 5-tier cap model
'free' ¦ 'standard' ¦ 'professional' stale comment | 5-tier comment | copy | selectedTier | ms.js 4291
legacy keys starter/premium | LEGIT — compat map keep | name | _LEGACY_TIER_MAP | launch_redemption 49
1T=$2 · allocs 6/10/20/50 · Founders 8/12/24/60 · slots 2/10/25/60/500 | keep-verify (no drift found in live code) | number | TIER_TUPPENCE_MONTHLY | anchor rows
Tuppence charged for AI use is cost-recovery | LEGIT under per-use canon | note | AI use is cost-recovery | eula 473 etc.
WhitePaper v2: AI uses + $5 Standard/$15 International + pack rates | PUBLISHED — superseded via Canon Addendum 1 rev 2 | rule | — | never edit
CX cost variants $5/$15 | recommend _ARCHIVE (AD-09) | number | \$5/mo | 3 Codices xlsx

## Matrix
TRACEABILITY MATRIX
Change-ID: | CC-002 |  | Resolved %: | 28.57% | (must reach 100% before the change is done)
Rows 5-7 are illustrative — delete and fill with this change's real (artifact x change-item) hits.
Artifact (file / path) | Class # | Change-item (term-map row) | Status | Owner | Verify method | Verified by | Date | Notes / N-A reason
Solar_Council_Codex_v4_8_DRAFT.docx (§11 + tbl9 + briefing AI text) | 1 | 5-tier + per-use AI + retire packs | edited | David | David | Fable (staged) | 2026-06-10 | Gate2+§12 — DRAFT staged; durations AD-12
MS:AGENT_BRIEFING.md L29 + L144-170 endpoint rows | 1 | packs + ai_pack_sessions + buy-pack + dev/credit ai_sessions | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged
MS:docs/PRINCIPLE_REQUIREMENTS.md A7+B6 infra | 1 | old buyer tiers | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | v1.2 DRAFT master
AA/CL/CX PRINCIPLE_REQUIREMENTS.md A7 | 1 | old buyer tiers | pending | Claude | grep-zero |  | 2026-06-10 | copies after approval
AA:AGENT_BRIEFING.md 89/93/95 + SESSION_START_PROMPT + AA:STATUS | 5 | pack-purchase UI language rows | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged
AdvertAgent AI_FUNCTIONS_SPEC.md | 5 | already canon | N-A | — | grep-zero | Fable (staged) | 2026-06-10 | reference doc for new wording
AdvertAgent AI_CostModel.xlsx | 6 | check for AI-uses/pack tokens | verified | Claude | grep-zero | Fable Sensor | 2026-06-10 | clean — 'packs amortize R1' cell = Tuppence top-up sense (legit, AD-17 note)
MS:Cost_Breakdown_GlobalLaunch.xlsx | 6 | Session-90 new model | N-A | — | grep-zero | Fable (staged) | 2026-06-10 | already canon; allocations spot-checked
CX cost variants (GlobalLaunch/MultiCity/Updated) | 6 | $5/$15 5-listings | pending | David | David |  | 2026-06-10 | AD-09 archive recommendation
eula_clean.html + eula_raw.html tier table 527-535 | 12 | buyer-tier table → 5-tier | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged; AD-10 pipeline
marketsquare.html 2210-2214 EULA block + 1120 button + 3040 pack + 2604/2607/2802/2805 sessions | 4 | 4 copy sets | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged file + diff
ms.js 11615 EULA mirror + 916/661 legacy params + 4291 comment | 4 | 3 sets | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged file + diff
marketsquare_admin.html 3783-84 | 4 | AI sessions panel | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged
bea_main.py ai_pack_sessions path 3115-3249 | 3 | retire legacy pack crediting | edited | David | smoke | Fable (staged) | 2026-06-10 | Gate 2 — staged diff, attended deploy
bea_main.py 1205/2610-21 ai_sessions registration credit | 3 | 3-free-sessions concept | edited | David | smoke | Fable (staged) | 2026-06-10 | AD-06 copy + code; staged diff
bea_main.py 3853-3873 coach charge + aa_buy_pack stub + 8154-58 nudge seeds | 3 | retired-model remnants | pending | David | smoke |  | 2026-06-10 | SCAN-14 queued; AD-03
launch_redemption.py + tier_resolvers.py + ai_service_tiers.py | 3 | already canon | N-A | — | grep-zero | Fable (staged) | 2026-06-10 | TIER_TUPPENCE_MONTHLY 6/10/20/50 verified
support.html 343-344 tier rows | 12 | Starter $5/Premium $15 → 5-tier | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged
5 outreach templates AI Coach uses (MS n8n set) | 7 | retired SKU | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged
5 outreach templates AI Coach uses (CL emailer set) | 7 | retired SKU | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged
intro_accepted/declined emails | 7 | (CC-001 rows cover) | N-A | — | — | Fable (staged) | 2026-06-10 | no CC-002 tokens
dashboards | 8 | (zero hits) | N-A | — | grep-zero | Fable (staged) | 2026-06-10 | clear
docs/LISTING_STATE_MACHINE.md + Architecture_Blueprint + SELL_FLOW + SESSION_NOTES + PLAN.md | 9 | historical spec docs w/ old tiers | pending | David | David |  | 2026-06-10 | AD-13: mark historical or sweep — recommendation logged
STATUS/CHANGELOG/BACKLOG/AUDIT_PROGRESS | 9 | self-referential | N-A | — | — | Fable (staged) | 2026-06-10 | legit
server copies | 10 | deployed counterparts | N-A | — | blocked | Fable (staged) | 2026-06-10 | no live access this run
memory: project_pricing_ai_canon | 11 | referenced in register, missing | edited | Claude | visual | Fable (staged) | 2026-06-10 | created this run
WhitePaper v2 (PUBLISHED) | 2 | AI uses + old tiers | N-A | David | — | Fable (staged) | 2026-06-10 | superseded via Canon Addendum 1 rev 2 — never edit
WhitePaper v3_4 + IP Brief v5/v6 + Strategy | 2 | (zero CC-002 tokens) | N-A | — | grep-zero | Fable (staged) | 2026-06-10 | already new-canon
AdvertAgent_Pricing_Model.xlsx | 6 | retired pack economy ($2 per 8-use pack etc.) | pending | David | David |  | 2026-06-10 | AD-17 — archive or rebuild per-use
marketsquare_admin.html 5248+5336 city-reach upsell cards | 4 | $5/month·Starter upsell ×2 | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged: from $12/month · paid plans (AD-18 reach pending)
bea_main.py 7891 multi-city 402 message | 3 | Starter $5/month error text | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged: paid subscription from $12/month
bea_main.py 4947-4990 + marketsquare.html 1120 wishlist Global SKU | 3 | $5/month Global subscription (PR-16/18) | pending | David | David |  | 2026-06-10 | AD-15 — separate SKU, fold/retire decision; allowlisted in proof
ms.js 10101 legacy coach wallet block | 4 | AI Coach Credits comment/function | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | comment retitled; function behaviour untouched
AA:SESSION_START_PROMPT.md + AA:STATUS.md legacy lines | 5 | pack endpoints/buttons + card titles | edited | Claude | grep-zero | Fable (staged) | 2026-06-10 | staged; AA STATUS L110 already notes OBSOLETE (legit)
PRINCIPLE_REQUIREMENTS divergence (v1.1 AA/CL/CX vs v1.2 MS) | 1 | copies out of sync since 17 May | pending | David | David |  | 2026-06-10 | AD-16 — v1_3 DRAFT staged as new master

## Artifact Classes
ARTIFACT-CLASS CHECKLIST — walk & grep every class; a class is clear only at zero hits
# | Class | What it includes | Grep clear? | Hits | Notes
1 | Canon & governance | Codex, Canon Addenda, PRINCIPLE_REQUIREMENTS, 4x AGENT_BRIEFING, ORCHESTRATION_POLICY, AUTONOMY_LADDER, all 5 CLAUDE.md | NO | 8 | Codex+briefings+PR
2 | IP / patent lineage | IP Brief (->v6), Patent Strategy v4, WhitePaper v3_4, Pre-Filing set, Claim Visuals. WhitePaper v2 PUBLISHED — Addendum only | YES | 0 | v2 via Addendum; v3_4/v5 clean
3 | BEA code | bea_main.py, ai_service_tiers.py, payments.py, tier_resolvers.py, value_resolvers, auth/db/storage, feature_flags.py, launch_redemption.py, smoke+tests | NO | 6 | 3 retired-model code paths
4 | FEA / apps | marketsquare.html, marketsquare_admin.html, ms.js, ms.css | NO | 8 | app copy sets
5 | AdvertAgent | AI_FUNCTIONS_SPEC, Functions Spec docx, Pricing_Model.xlsx, AI_CostModel.xlsx, Cost_Brief, Value_Benchmark, HMI_Spec, service/ | NO | 5 | AA briefing/status legacy lines
6 | Cost models (.xlsx) | Cost_Breakdown_GlobalLaunch (both copies), AdvertAgent xlsx pair, Codices cost variants | NO | 4 | CX variants old; MS canon
7 | Email templates | 16 in n8n/email_templates + CityLauncher emailer templates + n8n synced copies | NO | 10 | AI Coach uses x10
8 | Dashboards / ops pages | dashboard.html, orchestrator.html, citylauncher_ops.html, LAUNCH_READINESS_PLAN.html, /dashboard/summary doc-parse | YES | 0 | zero
9 | Session docs | STATUS, CHANGELOG, BACKLOG, AUDIT_PROGRESS (per project) | NO | 6 | historical spec docs
10 | Server-deployed copies | /var/www/marketsquare (index/admin/main/static + 4 parsed docs), launch.conf, CityLauncher .env | BLOCKED | 0 | no live access
11 | Memory | space MEMORY.md index + every relevant project_/feedback_ file | NO | 1 | memory file missing
12 | Public-facing copy | trustsquare.co homepage (Tuppence Wallet) + /support FAQ (mechanism + refund disclosure) | NO | 7 | eula+support